## Instructions
Corrective Action Plan:
Background/Overview
•The County Waiver Agency (CWA) has been made aware of ongoing/unresolved performance concerns related to enrollment timeliness. The CWA has not satisfactorily addressed the concerns identified and continues to fall short of contract requirements and performance expectations. •To assist the underperforming CWA in achieving compliance, the Wisconsin Department of Health Services (DHS) has discretion to direct the CWA to develop and implement a Corrective Action Plan. •The goal is improved performance and full compliance with the CWA's contractual obligations for enrollment timeliness. DHS is committed to this collaborative effort.
Instructions
Template may not be altered. Other than practical adjustments to column width or row height, CWA may not make any changes to this template. This Excel-based template is the tool by which DHS tracks and evaluates the CWA's progress.
Root Cause Analysis (RCA) Tab
•Root Cause Analysis is a precursor to developing the agency's corrective action plan and involves identifying the direct causes and precipitating circumstances and analyzing the CWA’s capacity to serve children who are referred, eligible to enroll, and enrolled. This exercise documents agency's investigation into the root causes of each performance concern and will help determine the best course for correction.
•The RCA will be used to set the framework for the proposed solutions, milestones, and benchmarks.
Corrective Action Plan (CAP) Tab
•As part of the CAP submission, the CWA must also outline the measurable corrective action steps. For each corrective action step, the CWA must identify the quantitative benchmarks, milestones, person(s) responsible, timelines, and evidencing strategies.
•Some examples of corrective action steps include, but are not limited to: -Perform staffing analysis to determine if internal policies and practices related to recruitment and hiring should be modified and the number of additional staff and caseload capacity needed to meet enrollment timelines. -Work with county leadership to prioritize staff resources and priority operations. -Sub-contract with a case management entity or another CWA for Support and Service Coordination services.
•Each corrective action proposed in the CAP tab auto-populates into a separate Corrective Action numbered tab. The CWA must provide a detailed plan for the milestones, evidencing strategy, person(s) responsible, and timelines to complete the corrective action.
•Examples of evidencing strategies include, but are not limited to, copies of job postings, revised caseload size policy, county board agenda, meeting minutes, and market rate analyses.
•The CWA must propose a completion date where all all corrective action steps will be implemented, and the CWA has evidenced that the rolling 6-month average of their dashboard data is at or below 100 days for two consecutive months.
•The status, planned and actual start and finish dates, and file names should not be filled in for the initial CAP submission. The CWA should fill in these columns during monthly reporting.
Monthly reports
Following DHS approval of the CWA's CAP, the CWA shall commence the plan and submit monthly progress reports on the Corrective Action tabs to evidence progress.
•The monthly reports include the status of each milestone, planned and actual start and end dates, and documentation outlined in the evidencing strategies section.
•CWAs must submit the file in a "clean" format; in good order, without activated filters or hidden rows or columns. The CWA must also submit any additional files for evidencing progress and indicate the appropriate file name under each corrective action. If there are DHS written comments, DHS will send the spreadsheet back to CWA. DHS will rename it pursuant to naming conventions. This practice permits continuity and effective issue tracking.
Report Naming Conventions: A. FORMAT: CWA YYYY CAP_Report_Submittal Date MM-DD-YY DESCRIPTION: CWA, YYYY year levied, Action Type (CAP), monthly report, submittal date MM-DD-YY Example for "ABCD" agency: ABCD 2024 CAP Report_11-07-24 B. When DHS adds comments to the report, the change is tracked by adding the suffix "_DHS" Example for "ABCD" agency: ABCD 2024 CAP Report 11-07-24_DHS CWA shall rename according to A (above) when submitting the following month's report.
Evaluation
DHS will monitor progress throughout the CAP. When all matters have been satisfactorily resolved and the CWA has demonstrated consistent, sustainable performance of its obligations for two consecutive months of dashboard data, the team will submit its findings and propose conclusion of the CAP to DHS leadership.
August 2024

## RCA
ROOT CAUSE ANALYSIS is a percursor to developing the CWA's corrective action plan. This exercise documents the CWA's investigation into the root causes of the performance concern.
Direct Causes The clear/primary cause(s). Were there situational factors that contributed to or exacerbated the non-compliance? You must include an analysis of your staff capacity to serve children who are referred, eligible to enroll, and enrolled.

## CAP
The CORRECTIVE ACTION PLAN includes the steps and timeline that the CWA will implement to achieve compliance.
Item No. | Corrective Action The corrective action step that will be implemented to address the causes and circumstances. | Benchmarks Set quantitative performance targets for each corrective action. Targets may be related to the number or percentage of kids waiting or average wait time. | Estimated Completion Date The date that the proposed solution will be complete.
1
2
3
4
5
Proposed CAP Completion Date:
The date that all corrective action steps will be implemented, and the CWA has evidenced that the rolling 6-month average of their dashboard data is at or below 100 days for two consecutive months.

## Corrective Action 1
Corrective Action #1: | 0 |  |  | MONTHLY REPORTING
Benchmark | 0
Milestones Outlines the specific steps and initiatives required to achieve the corrective action. | Evidencing Strategy How will progress be evidenced? Documentation, data, or other evidence. | Person(s) Responsible Include the name and title of accountable individual(s) for each milestone. | Estimated/Relational Mitigation Timeline Include start and end dates. Estimates and relative descriptions (once A, then B) are permitted here. | Status Options: Not started, on track, hold, warning, complete. | Planned Start Date | Actual Start Date | Planned Finish Date | Date of actual finish | File Names for Evidencing Progress Name of files attached to the monthly report submission that evidences progress.

## Corrective Action 2
Corrective Action #2: | 0 |  |  | MONTHLY REPORTING
Benchmark | 0
Milestones Outlines the specific steps and initiatives required to achieve the corrective action. | Evidencing Strategy How will progress be evidenced? Documentation, data, or other evidence. | Person(s) Responsible Include the name and title of accountable individual(s) for each milestone. | Estimated/Relational Mitigation Timeline Include start and end dates. Estimates and relative descriptions (once A, then B) are permitted here. | Status Options: Not started, on track, hold, warning, complete. | Planned Start Date | Actual Start Date | Planned Finish Date | Date of actual finish | File Names for Evidencing Progress Name of files attached to the monthly report submission that evidences progress.

## Corrective Action 3
Corrective Action #3: | 0 |  |  | MONTHLY REPORTING
Benchmark | 0
Milestones Outlines the specific steps and initiatives required to achieve the corrective action. | Evidencing Strategy How will progress be evidenced? Documentation, data, or other evidence. | Person(s) Responsible Include the name and title of accountable individual(s) for each milestone. | Estimated/Relational Mitigation Timeline Include start and end dates. Estimates and relative descriptions (once A, then B) are permitted here. | Status Options: Not started, on track, hold, warning, complete. | Planned Start Date | Actual Start Date | Planned Finish Date | Date of actual finish | File Names for Evidencing Progress Name of files attached to the monthly report submission that evidences progress.

## Corrective Action 4
Corrective Action #4: | 0 |  |  | MONTHLY REPORTING
Benchmark | 0
Milestones Outlines the specific steps and initiatives required to achieve the corrective action. | Evidencing Strategy How will progress be evidenced? Documentation, data, or other evidence. | Person(s) Responsible Include the name and title of accountable individual(s) for each milestone. | Estimated/Relational Mitigation Timeline Include start and end dates. Estimates and relative descriptions (once A, then B) are permitted here. | Status Options: Not started, on track, hold, warning, complete. | Planned Start Date | Actual Start Date | Planned Finish Date | Date of actual finish | File Names for Evidencing Progress Name of files attached to the monthly report submission that evidences progress.

## Corrective Action 5
Corrective Action #5: | 0 |  |  | MONTHLY REPORTING
Benchmark | 0
Milestones Outlines the specific steps and initiatives required to achieve the corrective action. | Evidencing Strategy How will progress be evidenced? Documentation, data, or other evidence. | Person(s) Responsible Include the name and title of accountable individual(s) for each milestone. | Estimated/Relational Mitigation Timeline Include start and end dates. Estimates and relative descriptions (once A, then B) are permitted here. | Status Options: Not started, on track, hold, warning, complete. | Planned Start Date | Actual Start Date | Planned Finish Date | Date of actual finish | File Names for Evidencing Progress Name of files attached to the monthly report submission that evidences progress.